## Steel Cost Adjustment Template
PROJECT TITLE
Steel Cost Adjustment Payment Calculation (for Use During Construction)
How to Use this Calculator
Monthy Calculation Data
| ITEM | QUANTITY | Bid Opening Date:
Date of Calculation:
Payment or Credit Calculation
Get Steel Materials Values
Initial Cost Basis (ICB)
Base Steel Materials Index Value (BV)
Monthly Steel Materials Index Value (MV)
| Pounds of Eligible Steel (WS) |  |  | 0
| Calculated Payment or Credit |  |  | #DIV/0!
CA = Cost Adjustment, dollars
MV = Monthly Steel Materials Index Value from BLS for the month determined above
BV = Base Steel Materials Index Value taken as the most recent value published on the BLS website on the day of bid opening.
ICB = Initial Cost Basis of steel
WS = Weight of steel eligible for cost adjustment
Calculate Payment
1. Enter Base Steel Materials Index Value (BV) at the beginning of the project.
( This Number Does NOT get revised )
2. Enter the Monthly Steel Materials Index Value (MV) each month when preparing that months Progress Estimate.
This sheet will calculate the dollars of PAYMENT or CREDIT
This is the amount of adjustment to be paid for the month. Note: Only those items included in the contract provisions are eligible for adjustment.
How is the Steel Cost Adjustment determined ?
1. If the MV is within ten-percent of the BV, there will be no adjustment. 2. If the MV is more than 110-percent of the BV, then:
CA = (((MV - BV) ÷ BV) - 0.10) × (ICB × WS)
3. If the MV is less than 90-percent of the BV, then
CA = (((MV - BV) ÷ BV) + 0.10) × (ICB × WS)
WPUSISTEEL1
GSP 1-09.3.OPT2.FR1
Note on B24: WEB LINK for Bureau of Labor Statistice web site to obtain Base and Monthly Steel Materials Index Value: https://data.bls.gov/timeseries/WPUSISTEEL1?include_graphs=false&output_type=column&years_option=all_years
Note on B26: Use a value of $0.40/lb. If the HQ Construction Office has approved an IBC different than $0.40, Enter the approved revised the Initial Cost Basis (ICB) amount.
Note on B27: BASE STEEL MATERIALS VALUE = The Base Steel Materials Index Value (BV) will be the most recent value published on the Bureau of Labor Statistics (BLS) website on the day of bid opening (even if listed as a preliminary value).
Note on B28: MONTHLY STEEL MATERIALS VALUE = The Monthly Steel Materials Index Value (MV) will be the final index value published on the BLS website for any month during the life of the contract.

## Fuel Cost Adjustment Template
Fuel Cost Adjustment Template
GSP1-09.3.OPT1.GR1
BASE FUEL COST |  |  |  | dollars | http://www.eia.gov/petroleum/gasdiesel/ |  |  | U.S. On-Highway Diesel Fuel Prices(dollars per gallon)
| Upper Threshold |  | 0 |  |  |  |  | West Coast less California
| Lower Threshold |  | 0
Monthly Fuel Cost |  |  |  | dollars | http://www.eia.gov/petroleum/gasdiesel/ |  |  | U.S. On-Highway Diesel Fuel Prices(dollars per gallon)
West Coast less California
ELIGIBLE BID ITEM | [5 empty] | UOM | Qty This Est. | Factor |  | Q
|  | Excavation Incl. Haul |  |  |  | CY |  | 0.7 | gal/cy | 0
|  | Excavation Incl. Haul - Area |  |  |  | CY |  | 0.7 | gal/cy | 0
|  | Borrow Incl. Haul |  |  |  | CY |  | 0.68 | gal/cy | 0
|  | Borrow Incl. Haul |  |  |  | Ton |  | 0.45 | gal/ton | 0
| Structure Excavation Class |  |  |  | Incl. Haul | CY |  | 0.7 | gal/cy | 0
| Crushed Surfacing |  |  |  |  | Ton |  | 0.7 | gal/ton | 0
| Crushed Surfacing |  |  |  |  | CY |  | 1.2 | gal/cy | 0
| Furnishing And Placing Crushed |  |  |  |  | CY |  | 1.2 | gal/cy | 0
| Furnishing And Placing Crushed |  |  |  | to No. 4 | SY |  | 0.02 | gal/sy | 0
| Furnishing And Placing Crushed Screening |  |  | No. 4 |  | SY |  | 0.002 | gal/sy | 0
| Planing Bitumiuous Pavement |  |  |  |  | SY |  | 0.09 | gal/SY | 0
| HMA Cl. |  | PG |  |  | Ton |  | 0.9 | gal/ton | 0
| HMA For |  |  |  |  | Ton |  | 0.9 | gal/ton | 0
| Commercial HMA |  |  |  |  | Ton |  | 0.9 | gal/ton | 0
| Cement Concrete Pavement |  |  |  |  | CY |  | 1.2 | gal/cy | 0
| Cement Concrete Pavement - Including Dowels |  |  |  |  | CY |  | 1.2 | gal/cy | 0
| Concrete Class |  |  |  |  | CY |  | 1.2 | gal/cy | 0
| Commercial Concrete |  |  |  |  | CY |  | 1.2 | gal/cy | 0
| Superstructure |  |  |  |  | L.S. |  | 0.005 | gal/dollar | 0
| St. Reinf. Bar |  |  |  |  | LB. |  | 0.004 | gal/lb | 0
| Epoxy-Coated St. Reinf. Bar |  |  |  |  | LB. |  | 0.004 | gal/lb | 0
[9 empty] | Sum Of Q | 0
| Monthly Fuel Cost Payment/Credit | [5 empty] | 0
NOTE:
Base Fuel Cost = Weekly U.S. On-Highway Diesel Fuel Prices (Dollars per Gallon) dated on the nearest Monday occuring three weeks prior to bid opening.
Monthly Fuel Cost = Most recent Monthly U.S. On-Highway Diesel Fuel Prices (Dollars per Gallon).
Calculation Factors on this form last revised date: 4/6/2023

## Fuel Cost Instructions
Fuel Cost Adjustment Worksheet Instructions
Initial Setup
1) |  | Go to the DOE website listed below, scroll down to U.S. On-Highway Diesel Fuel Prices (dollars per gallon), and click on West Coast less California.
| a. | On the next page go to the line "Diesel (On-Highway) - All Types" and Click on "View History".
| b. | On this page set the "Period" to Weekly and get the Weekly West Coast (PADD 5) Except California No 2 Diesel Retail Prices (Dollars per Gallon) for the nearest Monday occurring three weeks prior to the date on which the bids were opened.
| c. | Enter this as the Base Fuel Cost and the spreadsheet will calculate the 10% over/under for you.
2) |  | Enter any required descriptions for eligible items from your contract (i.e. HMA Cl, Surfacing type, Concrete Class, etc.). Only those items listed are eligible. If you have more than one of any eligible item, you can insert a line and copy/paste the item line into the worksheet.
Progress Estimate
1) |  | Go to the DOE website listed below, scroll down to U.S. On-Highway Diesel Fuel Prices (dollars per gallon), and click on West Coast less California.
| a. | On the next page go to the line "Diesel (On-Highway) - All Types" and Click on "View History".
| b. | On this page set the "Period" to Monthly and get the Monthly West Coast (PADD 5) Except California No 2 Diesel Retail Prices (Dollars per Gallon) .
| c. | Enter this as the Monthly Fuel Cost.
2) |  | Enter the quantities of those eligible items to be paid on this estimate. The worksheet will calculate the credit/payment to be made on this estimate.
Resource
http://www.eia.gov/petroleum/gasdiesel/

## Asphalt Cost Adjustment
Asphalt Cost Adjustment Template
BASE COST
| UPPER THRESHOLD | 0 |  | Note: Base Cost and Current Reference Cost to be taken from WSDOT website below:
| LOWER THRESHOLD | 0 |  | http://www.wsdot.wa.gov/biz/construction/pdf/referencecosts.pdf
CURRENT REFERENCE COST
ELIGIBLE BID ITEM | [5 empty] | UOM | Qty This Est.
| HMA Cl. |  | PG |  |  | Ton
| HMA for Approach Cl. |  | PG
| HMA for Preleveling Cl. |  | PG
| HMA for Pavement Repair Cl. |  | PG
Commercial HMA
[5 empty] | Sum of Quantities |  | 0
| Asphalt Cost Price Adjustment |  |  |  | 0
For Current Estimate (Payment/Credit)
NOTE
Base Cost = the reference cost posted on the Agency website for the period immediately preceding the bid opening date.
Current Reference Cost = the most current cost posted on the Agency website on the day of estimate cut-off.

## Asphalt Cost Instructions
Asphalt Cost Price Adjustment Worksheet Instructions
Initial Setup
1) | Go to the WSDOT Construction Office website listed below to get the base asphalt cost (the cost posted with an effective date immediately prior to the bid opening date as specified in the contract - for either Western Washington or Eastern Washington ) and enter it. The worksheet will calculate the percent over/under for you.
2) | Enter any required descriptions for eligible items from your contract (i.e. HMA Cl. 1/2 inch). Only those items listed are eligible. If you have more than one of any eligible item, you can insert a line and copy/paste the item line into the worksheet.
Progress Estimate
1) | Go to the WSDOT website listed below to get the current reference asphalt cost (most current cost posted on the estimate cut-off date (5th or 20th) - for either Western Washington or Eastern Washington) and enter it.
2) | Enter the quantities of those eligible items to be paid on this estimate. The worksheet will calculate the credit/payment to be made on this estimate.
Resource
http://www.wsdot.wa.gov/Business/Construction/AsphaltBinderReferenceCost.htm

## CRS-2P Cost Adjustment
CRS-2P Cost Adjustment Template
BASE COST |  | 0
| UPPER THRESHOLD | 0 | Note: Base Cost and Current Reference Cost to be taken from WSDOT website below:
| LOWER THRESHOLD | 0 | http://www.wsdot.wa.gov/biz/construction/pdf/referencecosts.pdf
CURRENT REFERENCE COST |  | 0
ELIGIBLE BID ITEM |  |  |  |  | UOM | Qty This Est.
| CRS-2P |  |  |  | Ton (Q) | 0
| Monthly CRS-2P Cost Payment/Credit |  |  | 0
NOTE
Base Cost = the reference cost posted on the Agency website for the period immediately preceding the bid opening date.
Current Reference Cost = the most current cost posted on the Agency website on the day of estimate cut-off.

## CRS-2P Instructions
CRS-2P Cost Price Adjustment Worksheet Instructions
Initial Setup
1) | Go to the WSDOT Construction Office website listed below to get the base asphalt cost (the cost posted for the period specified in the contract - for either Western Washington or Eastern Washington ) and enter it. The worksheet will calculate the % over/under for you.
Progress Estimate
1) | Go to the WSDOT website listed below to get the current reference asphalt cost (most current cost posted at the time of estimate preparation - for either Western Washington or Eastern Washington) and enter it.
2) | Enter the quantities of CRS-2P to be paid on this estimate. The worksheet will calculate the credit/payment to be made on this estimate.
Resource
http://www.wsdot.wa.gov/biz/construction/pdf/referencecosts.pdf